## Sheet1
Fitur View Status
Task | Duration (hour) | PIC | Hours
HTML Mockup | 3 | MA | 3
Front End Coding | 3 | BL | 3
Design Table | 1 | SV | 1
Back End Coding | 3 | EY | 3
Testing | 2 | AB | 2
Total Hours: |  |  | 12
Fitur Update Status
Task | Duration (hour) | PIC | Hours
HTML Mockup | 3 | MA | 3
Front End Coding | 3 | FS | 3
Design Table | 1 | SV | 1
Back End Coding | 3 | EY | 3
Testing | 2 | MY | 2
Total Hours: |  |  | 12
Fitur View Sales
Task | Duration (hour) | PIC | Hours
HTML Mockup | 3 | MA | 3
Front End Coding | 3 | BL | 3
Design Table | 1 | SV | 1
Back End Coding | 3 | EY | 3
Testing | 2 | AB | 2
Total Hours: |  |  | 12
Fitur View Customer Review
Task | Duration (hour) | PIC | Hours
HTML Mockup | 3 | MA | 3
Front End Coding | 3 | FS | 3
Design Table | 1 | SV | 1
Back End Coding | 3 | EY | 3
Testing | 2 | MY | 2
Total Hours: |  |  | 12