## Sprint Review
Sprint Review Group 3 :
Who invated :
| 1. Reza Arinanda |  | 1801381853 | Scram Master
| 2. Martinus |  | 1801379123
| 3. Jeffry Cik |  | 1801379842
| 4. Edmundus Valin |  | 1801383114
| 5. Brian Bevinius |  | 1801395000
| 6. Edwin NG |  | 1801416106
| 7. Fedriek Chandra |  | 1801400530
Schedule Activity :
Task |  |  | Meeting 1 | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Meeting 6
Mock Up Website |  |  | 13 | 8 | 6 | 5 | 0 | 0
Database Design |  |  | 12 | 10 | 6 | 3 | 0 | 0
Login |  |  | 3 | 2 | 0 | 0 | 0 | 0
View Order |  |  | 6 | 5 | 5 | 3 | 0 | 0
View Bill Request |  |  | 6 | 5 | 5 | 3 | 0 | 0
View Custommer Item Request |  |  | 3 | 2 | 2 | 2 | 0 | 0
View Stock |  |  | 5 | 5 | 5 | 5 | 5 | 5
View Item Recipe |  |  | 2 | 2 | 2 | 2 | 2 | 2
Update Status Order |  |  | 3 | 3 | 3 | 2 | 2 | 0
View Custommer Review |  |  | 10 | 8 | 6 | 5 | 3 | 0
View Custommer Bill |  |  | 2 | 2 | 2 | 1 | 0 | 0
Request Bill |  |  | 3 | 3 | 3 | 2 | 0 | 0
View Ingredients each item |  |  | 6 | 6 | 6 | 6 | 6 | 0
Show Picture Menu |  |  | 2 | 2 | 2 | 0 | 0 | 0
View Duration of each menu |  |  | 2 | 2 | 2 | 2 | 2 | 0
View Status Order |  |  | 2 | 2 | 2 | 1 | 1 | 0
Filtering Ingredients Low Stock |  |  | 5 | 5 | 5 | 5 | 5 | 5
View Sales Each Day |  |  | 6 | 6 | 6 | 6 | 4 | 0
View Item Trend |  |  | 5 | 5 | 5 | 4 | 4 | 0
View Ingredients Expire list |  |  | 2 | 2 | 2 | 2 | 2 | 2
Total |  |  | 98 | 85 | 75 | 59 | 36 | 14
who does what :
Order menu |  |  |  | View Bill |  |  | Review Item and Restaurant
Task |  | Pic | Estimated | Task | Pic | Estimated | Task | Pic | Estimated
Mock up web |  | Edmund | 2 jam | Mock up web | Edmund | 2 jam | Mock up web | Edmund, Martinus | 3 jam
Content |  | Brian | 4 jam | Code HTML | Edwin, Fedrick | 3 jam | Code HTML | Edwin, Fedrick | 3 jam
Code HTML |  | Edwin | 4 jam | Code CSS | Jeffry, Brian | 3 jam | Code CSS | Jeffry, Brian | 3 jam
Code CSS |  | Jeffry, Brian | 5 jam | Tester | Brian | 2 jam | Tester | Brian | 2 jam
Javascript |  | Martinus | 5 jam | PHP Code | Reza | 5 jam | PHP Code | Reza | 9 jam
Tester |  | Frederick | 2 jam | Total |  | 15 jam | Total |  | 20 jam
PHP Code |  | Reza | 6 jam
Total |  |  | 28 jam
View Costumer Bill Request |  |  |  | Request Bill
Task |  | Pic | Estimated | Task | Pic | Estimated
Mock up web |  | Edmund, Martinus | 4 jam | Mock up web | Edmund | 2 jam
Content |  | Frederick | 3 jam | Code HTML | Edwin, Fedrick | 3 jam
Code HTML |  | Edwin | 2 jam | Code CSS | Jeffry, Brian | 3 jam
Code CSS |  | Jeffry, Brian | 2 jam | Tester | Brian | 2 jam
Tester |  | Brian | 2 jam | PHP Code | Reza | 5 jam
PHP Code |  | Reza | 7 jam | Total |  | 15 jam
Total |  |  | 20 jam

## Daily Scram
Task | Meeting 1 | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Meeting 6
Mock Up Website | 13 | 8 | 6 | 5 | 0 | 0
Database Design | 12 | 10 | 6 | 3 | 0 | 0
Login | 3 | 2 | 0 | 0 | 0 | 0
View Order | 6 | 5 | 5 | 3 | 0 | 0
View Bill Request | 6 | 5 | 5 | 3 | 0 | 0
View Custommer Item Request | 3 | 2 | 2 | 2 | 0 | 0
View Stock | 5 | 5 | 5 | 5 | 5 | 5
View Item Recipe | 2 | 2 | 2 | 2 | 2 | 2
Update Status Order | 3 | 3 | 3 | 2 | 2 | 0
View Custommer Review | 10 | 8 | 6 | 5 | 3 | 0
View Custommer Bill | 2 | 2 | 2 | 1 | 0 | 0
Request Bill | 3 | 3 | 3 | 2 | 0 | 0
View Ingredients each item | 6 | 6 | 6 | 6 | 6 | 0
Show Picture Menu | 2 | 2 | 2 | 0 | 0 | 0
View Duration of each menu | 2 | 2 | 2 | 2 | 2 | 0
View Status Order | 2 | 2 | 2 | 1 | 1 | 0
Filtering Ingredients Low Stock | 5 | 5 | 5 | 5 | 5 | 5
View Sales Each Day | 6 | 6 | 6 | 6 | 4 | 0
View Item Trend | 5 | 5 | 5 | 4 | 4 | 0
View Ingredients Expire list | 2 | 2 | 2 | 2 | 2 | 2
Total | 98 | 85 | 75 | 59 | 36 | 14
ESTIMATED EFFORT HOURS REMAINING
TEAM MEETING WITHIN A SPRINT

## SPRINT BACKLOG
Order menu |  |  | View Bill |  |  |  | Review Item and Restaurant
Task | Pic | Estimated | Task |  | Pic | Estimated | Task | Pic | Estimated
Mock up web | Edmund | 2 jam | Mock up web |  | Edmund | 2 jam | Mock up web | Edmund, Martinus | 3 jam
Content | Brian | 4 jam | Code HTML |  | Edwin, Fedrick | 3 jam | Code HTML | Edwin, Fedrick | 3 jam
Code HTML | Edwin | 4 jam | Code CSS |  | Jeffry, Brian | 3 jam | Code CSS | Jeffry, Brian | 3 jam
Code CSS | Jeffry, Brian | 5 jam | Tester |  | Brian | 2 jam | Tester | Brian | 2 jam
Javascript | Martinus | 5 jam | PHP Code |  | Reza | 5 jam | PHP Code | Reza | 9 jam
Tester | Frederick | 2 jam | Total |  |  | 15 jam | Total |  | 20 jam
PHP Code | Reza | 6 jam
Total |  | 28 jam
View Costumer Bill Request |  |  | Request Bill
Task | Pic | Estimated | Task |  | Pic | Estimated
Mock up web | Edmund, Martinus | 4 jam | Mock up web |  | Edmund | 2 jam
Content | Frederick | 3 jam | Code HTML |  | Edwin, Fedrick | 3 jam
Code HTML | Edwin | 2 jam | Code CSS |  | Jeffry, Brian | 3 jam
Code CSS | Jeffry, Brian | 2 jam | PHP Code |  | Reza | 5 jam
Tester | Brian | 2 jam | Tester |  | Brian | 2 jam
PHP Code | Reza | 7 jam | Total |  |  | 15 jam
Total |  | 20 jam
SPRINT BACKLOG KELOMPOK 3
|  |  | TOTAL JAM | 98

## Sprint Retrospective
SPRINT RETROSPECTIVE - TEAM 03
What worked well? |  | What didn't work well? | Where are some opportunities to do things differently
THINGS TO KEEP DOING |  | THINGS TO STOP DOING | THINGS TO TRY
Fix Promo Slider (Image slider) |  | Create item recipe view feature | Change website theme (dark to simple)
Fix CSS |  | Create add item recipe feature | Use another framework for compatibility
Create more menu items (content) |  | Item and recipe detail database integration | Create new header image
Fix bill menu view |  |  | Add more options for responsiveness
Create total sales view |  |  | View item rating and recommendation
Fix rating logic (sum to average) |  |  | Add customer wishlist feature
Add more payment options (optional)
Add coupon feature
Add live events feature
= Important things